SafetyMEG EHS Platform Project Delivery Timeline & Statement of Work Milestone 1: UI/UX Enterprise Overhaul ¦ Milestone 2: EHS Operational Expansion CONFIDENTIAL · Prepared for Client Review · March 2026

# 1. Executive Overview

SafetyMEG is an ambitious, enterprise-grade Environment, Health & Safety (EHS) platform that already stands well above the typical starting point. With a fully authenticated React + TypeScript SPA frontend, a Hono + SQLite backend hosting over 66 runtime route modules, 119 UI components, 95 page files, 52 backend test suites, and front-end Playwright E2E coverage — this platform has been built with the depth and breadth that would take most teams years to produce from scratch.

What has been achieved so far is genuinely impressive: real-world incident lifecycle management, AI-powered training generation, Permit-to-Work workflows, compliance calendar and standards cross-referencing, predictive safety scoring, mobile sync infrastructure, and much more. The foundation is solid, the architecture is production-oriented, and the domain coverage is already competitive with mid-tier commercial EHS products.

This document defines the next two milestones of work — agreed between the development team and the client — that will carry SafetyMEG to full enterprise polish and full EHS operational capability. Both milestones are compressed into an accelerated 8-week delivery window, made possible by the development team's deep existing familiarity with the codebase.

📌 Binding SOW: This Statement of Work is the single source of truth for both milestones. Any ambiguity during execution will be resolved by referring back to this document. Both parties commit to this scope, timeline, and payment schedule.

## 1.1 Document Purpose

- Define all work items for Milestone 1 (UI/UX Enterprise Overhaul) in exhaustive detail.

- Define all work items for Milestone 2 (EHS Operational Expansion + AI Intelligence) in exhaustive detail.

- Establish a precise, week-by-week delivery timeline compressing 18–20 weeks of standard work into 8 weeks.

- Define the progress-reporting cadence (2 submissions per week) and client review process.

- Provide a transparent market-value comparison — what this work would cost elsewhere vs. what we are charging.

- Justify our pricing and introduce our optional low-cost post-launch maintenance offering.

## 1.2 Project Summary Stats

| Item | Detail |
| --- | --- |
| Platform Name | SafetyMEG — Enterprise EHS Platform |
| Current State | 95 frontend pages, 66 backend route modules, 119 components, 52 test suites |
| Milestone 1 Focus | Full UI/UX Design System Overhaul — ~40+ pages & all components |
| Milestone 2 Focus | EHS Operational Expansion — 10 feature modules + technical debt |
| Milestone 1 Duration | 2 Weeks (Compressed from 5) |
| Milestone 2 Duration | 6 Weeks (Compressed from 13) |
| Total Timeline | 8 Weeks — with 1 buffer week for communication/edge cases |
| Launch Ready After | Week 7 — fully production-deployable; Week 8 is final hardening buffer |
| Payment Structure | Weekly installments — 2 progress submissions per week |
| Total Project Fee | $1,750 USD (Market Value: $15,000–$20,000) |
| Per-Submission Deliverables | Progress Report PDF + Source Code (Git) + Live Staging Link |

# 2. Payment Schedule & Progress Reporting

## 2.1 Weekly Payment Structure

To ease budget pressure and keep progress fully accountable, all payments are structured on a weekly basis. Each week you only pay for that week's deliverables — there are no large upfront lump sums. Every week's payment unlocks the following week's development. This ensures your investment is always protected by verified, tested, deployed progress.

💡 Why Weekly Payments Work For You: Instead of paying $1,750 all at once, you pay small weekly amounts. Each payment is backed by 2 tangible deliveries that week (report PDF + source code + staging link). If at any point you are dissatisfied, you can pause — you will never have overpaid for undelivered work. This is designed to give you full control and peace of mind.

| Week | Milestone | Key Deliverables | Payment (USD) |
| --- | --- | --- | --- |
| Week 1 | M1 | Design tokens, typography, color system, theme fix, brand fix | $75 |
| Week 2 | M1 ✅ Final | Component library, skeletons, toast, mobile responsiveness, QA | $75 |
| Week 3 | M2 | Module 3 (Audit Scheduling) + Module 4 (Training Matrix) | $275 |
| Week 4 | M2 | Module 1 (AI Incident Classification + OCR) + Module 2 (AI CAPA) | $275 |
| Week 5 | M2 | Module 5 (Asset Registry + LOTO) + Module 6 (Bowtie Builder) | $275 |
| Week 6 | M2 | Module 7: React Native App — Part 1 (Bootstrap, Offline, QR, Voice) | $275 |
| Week 7 | M2 | Module 7: React Native App — Part 2 (Camera AI, Push, Signatures) | $275 |
| Week 8 | M2 ✅ Final | Modules 8–10 + All Technical Debt + Final Production Deploy | $325 |
| TOTAL | — | Full enterprise EHS platform — production-ready | $1,750 |

Note: Final week payment ($325) is due upon client sign-off of the complete Milestone 2 delivery.

## 2.2 Per-Submission Deliverables

Every week includes 2 structured progress submissions. No specific days are fixed — submissions happen at natural delivery points during the week. Each submission includes all three of the following mandatory deliverables:

| Deliverable | Description |
| --- | --- |
| 📋 Progress Report PDF | A structured PDF covering: tasks completed, tasks in progress, blockers (if any), and next steps. Delivered professionally formatted. |
| 💻 Source Code (Git) | All code committed to the project repository with clean, descriptive commit messages. Client has read access at all times. |
| 🔗 Live Staging Link | A working staging URL where the client can log in, explore newly implemented features, and provide feedback. |

⏳ Feedback Window: Client has 3 business days to review each submission and provide feedback. Silence beyond 3 business days constitutes implicit acceptance of that delivery cycle's work.

## 2.3 Progress Report Schedule

Two progress reports are issued per week. Exact timing is flexible and driven by development completion, not fixed calendar days.

| Report # | Week | Milestone | What Is Deployed for Testing |
| --- | --- | --- | --- |
| PR-01 | Week 1 — Mid | M1 | Design system tokens, typography fixes, color palette on all pages |
| PR-02 | Week 1 — End | M1 | Dark/light theme persistence fixed, brand/logo fix, button color unification |
| PR-03 | Week 2 — Mid | M1 | SM* Component Library live — buttons, forms, cards globally replaced |
| PR-04 | Week 2 — End (M1 Final) | M1 ✅ | Full M1 build — skeleton loaders, toast, mobile responsiveness, QA complete |
| PR-05 | Week 3 — Mid | M2 | Module 3: Audit Scheduling Engine + BullMQ setup live on staging |
| PR-06 | Week 3 — End | M2 | Module 4: Training Matrix + Certification Expiry Engine live |
| PR-07 | Week 4 — Mid | M2 | Module 1: AI Incident Classification + OCR/NLP pipeline live |
| PR-08 | Week 4 — End | M2 | Module 2: AI CAPA Root Cause + Prioritization; S3/R2 provisioned |
| PR-09 | Week 5 — Mid | M2 | Module 5: Asset Registry + QR Code + LOTO Templates live |
| PR-10 | Week 5 — End | M2 | Module 6: Full Bowtie Builder + AI Bowtie Generation live |
| PR-11 | Week 6 — Mid | M2 | Mobile App Bootstrap + Offline Sync + QR + Voice-to-Incident |
| PR-12 | Week 6 — End | M2 | Mobile App Camera AI + Push Notifications + Digital Signatures |
| PR-13 | Week 7 — Mid | M2 | Module 8: Automation Engine + Module 9: ESG Carbon Dashboard |
| PR-14 | Week 7 — End | M2 | Module 10: SSO/HRIS/ERP Integrations + API Versioning |
| PR-15 | Week 8 — Mid | M2 | PostgreSQL migration, repo pattern, multi-tenant isolation complete |
| PR-16 | Week 8 — Final | M2 ✅ | Full production-ready deploy — all modules live, all tech debt resolved |

MILESTONE 1 UI/UX Enterprise Overhaul · Design System · Component Library · Theme · Responsiveness

# 3. Milestone 1 — UI/UX Enterprise Overhaul

Timeline: Weeks 1–2 (2 Weeks)  |  Total: $150 | After Milestone is totally done

The SafetyMEG platform currently has ~95 frontend pages, 119 components, and 13 service files. While the underlying functionality is strong, the visual presentation has the inconsistencies common to AI-assisted development: varied button styles, inconsistent typography scales, broken light/dark theme persistence, layout fragmentation on mobile, and no unified component library. Enterprise clients judge a product in the first 5 seconds — this milestone ensures SafetyMEG looks and feels exactly like the Cority, Intelex, and VelocityEHS platforms it competes with.

## 3.1 Week 1 — Design Tokens, Color System, Theme & Brand

Duration: 5 working days  |  Reports: PR-01 (mid-week) + PR-02 (end of week)

### Task 1.1 — Design Token System

Create a single source-of-truth design token file (tokens.ts or tailwind.config.ts extension):

- Spacing scale: 4, 8, 12, 16, 20, 24, 32, 40, 48, 64px

- Typography scale: xs(12), sm(14), base(16), lg(18), xl(20), 2xl(24), 3xl(30), 4xl(36)

- Border-radius tokens: sm(4px), md(8px), lg(12px), xl(16px), full(9999px)

- Shadow tokens: card, modal, dropdown, none

- Animation duration tokens: fast(150ms), normal(250ms), slow(400ms)

### Task 1.2 — Typography Standardization

Audit all 95 page files and 119 component files for typography inconsistencies. Apply uniform heading hierarchy (H1→H2→H3→body) using the token system across all pages including: Dashboard, IncidentReporting, InjuryReport, BowTieAnalysis, TrainingManagement, RiskAssessment, RiskRegister, PermitToWork, and all 40+ primary pages.

### Task 1.3 — Core Color Palette & Brand Identity

- Primary: Deep Navy (#0D2137) — headers, primary text, strong CTAs

- Accent / Brand: Teal (#00A89D) — active states, links, highlight borders

- Secondary: Slate Gray (#475569) — body text, secondary labels

- Success: Green (#16A34A) — pass/compliant/resolved states

- Warning: Amber (#F59E0B) — overdue, caution, pending states

- Danger: Red (#DC2626) — critical incidents, failed states, errors

### Task 1.4 — Dark/Light Theme Persistence Fix

The current theme state resets to dark mode on navigation. This is a critical UX bug. Fix includes ThemeProvider via Zustand with localStorage persistence, removal of all page-level hardcoded dark/light class overrides, and theme toggle in top navigation bar persisting across all sessions.

### Task 1.5 — Logo & Button Color Unification

Create inverted logo for dark theme. Standardize all primary CTA buttons to Teal, destructive actions to Red, and apply across all 40+ pages including IncidentReporting, AuditManagement, PermitToWork, TrainingManagement, and all remaining pages.

| Week 1 Deliverables | Status |
| --- | --- |
| Design token file committed to repository | Delivered in PR-01 |
| Typography pass complete on all 40+ pages | Delivered in PR-01 |
| Core color palette in Tailwind config | Delivered in PR-02 |
| Dark/light theme persistence fixed on all routes | Delivered in PR-02 |
| Button color unified across all pages | Delivered in PR-02 |
| Logo fix deployed (dark + light theme variants) | Delivered in PR-02 |

## 3.2 Week 2 — Component Library, Loaders, Toast & Mobile

Duration: 5 working days  |  Reports: PR-03 (mid-week) + PR-04 (Milestone 1 Final)

### Task 2.1 — Build SafetyMEG Core Component Library

Create the following shared components under frontend/src/components/ui/:

- SMButton — variants: primary, secondary, ghost, danger, icon-only; sizes: sm, md, lg; loading state

- SMInput — text, email, password, number, textarea; label, error, helper text; focus ring in teal

- SMSelect — single & multi-select with search; consistent dropdown styling

- SMDatePicker — date and date-range picker with calendar popup

- SMCard — header slot, body slot, footer slot; light/dark mode aware

- SMBadge — variants: success, warning, danger, neutral, teal; sizes: sm, md

- SMAlert — info, success, warning, danger variants with dismiss

- SMModal — accessible, focus-trapped modal with header, body, footer slots

- SMDrawer — side drawer (left/right) for mobile and desktop

- SMTable — sortable, filterable, paginated data table component

- SMTabs, SMTooltip, SMAvatar, SMPageHeader, SMEmptyState, SMStatusDot

### Task 2.2 — Replace All Ad-Hoc Components Globally

Replace all existing button, input, card, and modal implementations across all 95 pages:

- Pass 1: Replace all button implementations (60+ instances across pages)

- Pass 2: Replace all form input implementations (80+ instances)

- Pass 3: Replace all card/panel implementations (40+ instances)

- Pass 4: Replace all modal and drawer implementations (25+ instances)

- Pass 5: Replace all badge/status implementations (50+ instances)

### Task 2.3 — Skeleton Loaders & Toast System

Replace all blank-screen loading states with LinkedIn/Notion-style animated shimmer skeletons on Dashboard, IncidentList, TrainingManagement, AuditManagement, RiskRegister, and all 10+ list/table pages. Implement global toast notification system (success/error/warning/info, stacked up to 3).

### Task 2.4 — Mobile Responsiveness & Final QA

Complete mobile audit for all 40+ pages. Target: zero horizontal scrolling on 320px–1024px viewports. Final QA pass: WCAG AA compliance, cross-browser (Chrome, Firefox, Safari, Edge), device test on iPhone SE, iPhone 14, iPad, Desktop 1440px.

| Milestone 1 Final Deliverables | Status at Handover |
| --- | --- |
| Design token system committed to repository | Complete |
| Tailwind config with full color palette | Complete |
| Dark/light theme persists on all routes | Complete |
| Centralized SM* component library (16 components) | Complete |
| All buttons, inputs, cards, modals replaced globally | Complete |
| Skeleton loaders on all data-heavy pages | Complete |
| Global toast notification system | Complete |
| Mobile responsiveness — all 40+ pages (0 horizontal scroll) | Complete |
| Logo fixed for dark and light themes | Complete |
| Typography standardized — all pages | Complete |
| Accessibility pass (WCAG AA, focus, aria-labels) | Complete |
| Component library documentation in /docs/ | Complete |
| Full staging deployment with verified login | Delivered to client |

MILESTONE 2 EHS Operational Expansion · AI Intelligence · Mobile App · Enterprise Integrations

# 4. Milestone 2 — EHS Operational Expansion

Timeline: Weeks 3–8 (6 Weeks)  |  Payment: ~$275/week  |  Total: $1,600

Milestone 2 evolves SafetyMEG from a polished platform into a fully operational enterprise EHS system competitive with Cority, Intelex, and VelocityEHS. It adds ten feature modules, addresses all critical technical debt, and delivers a React Native mobile application. The modules are delivered in priority order for maximum business value per week. If the work is done before the timeline and has been verified then the payment will be done accordingly.

## 4.1 Week 3 — Module 3 (Audit Scheduling) + Module 4 (Training Matrix)

Reports: PR-05 (Module 3 complete) + PR-06 (Module 4 complete)

### Module 3: Audit Scheduling Engine

- New DB tables: audit_schedules (RRULE strings, assigned sites) + audit_programs (multi-site groupings)

- BullMQ + Redis background job worker: daily cron generates audit instances automatically from RRULE

- API: GET/POST/PUT/DELETE /api/audits/schedule + multi-site compliance report endpoint

- Frontend: AuditScheduleBuilder.tsx (RRULE builder), AuditCalendarView.tsx, MultiSiteComplianceReport.tsx

- AI Checklist Generation: POST /api/ai/audit-form/generate-checklist — structured JSON checklist from standard + scope

- Conditional Form Logic Builder: drag-and-drop if/then logic stored as JSON schema, evaluated client-side

### Module 4: Training Matrix + Certification Expiry Engine

- New DB tables: training_matrix (role + site + hazard → required competencies) + certification tracking

- Training Gap API: GET /api/training/matrix/gaps?worker_id= and ?site_id= endpoints

- Certification Expiry Engine: BullMQ daily cron scans 90/60/30/7-day expiry windows + email reminders

- SCORM / xAPI External LMS Support: POST /api/training/xapi/statements — accepts external LMS completions

- Frontend: TrainingMatrix.tsx (grid: green=complete, red=gap, amber=expiring) + SkillGapReport.tsx

## 4.2 Week 4 — Module 1 (AI Incident Classification) + Module 2 (AI CAPA)

Reports: PR-07 (Module 1 complete) + PR-08 (Module 2 + S3/R2 setup)

### Module 1: AI Incident Classification + Evidence OCR

- New DB tables: classification_rules (OSHA 300 / WSIB logic as JSON), incident_evidence, injury_details

- AI Classification: POST /api/incidents/:id/classify — LLM + rules hybrid, outputs severity/category/confidence

- Evidence Intelligence (OCR + NLP): image upload → OCR text → NLP entity extraction → populate hazards/causes/controls

- Incident Timeline: GET /api/incidents/:id/timeline — chronological event log with all state changes

- Transactional Email NE-01: Incident Created Alert to reporter + assigned supervisor

### Module 2: AI CAPA Intelligence

- AI Root Cause Suggestions: auto-call AI with incident description, outputs 5-Why or Fishbone structured data

- AI Corrective Action Recommendations: POST /api/capa/:id/ai-recommend — ranked actions with effectiveness score

- Predictive CAPA Prioritization: ML scoring f(incident_severity, overdue_days, recurrence, site_risk_level)

- Transactional Email NE-02: CAPA Overdue Alert — daily cron to CAPA owner + department manager

- S3/R2 File Storage: Provision Cloudflare R2 for all evidence photos, SDS PDFs, and digital signatures

## 4.3 Week 5 — Module 5 (Asset Registry) + Module 6 (Bowtie Builder)

Reports: PR-09 (Module 5 complete) + PR-10 (Module 6 complete)

### Module 5: Asset & Equipment Safety Management

- New DB table: assets (id, name, type, location, serial, qr_token, purchase_date, status, risk_score)

- QR code generation: POST /api/assets/:id/qr-code — returns PNG, used for mobile scanning

- Inspection intervals + calibration tracking: DB tables + BullMQ overdue alerts

- LOTO Templates: procedure_steps[], energy_sources[], required_ppe[] — mobile workers scan QR to view LOTO before work

- AI-Flagged High-Risk Assets: risk_score = f(missed inspections, failures, age, calibration overdue)

### Module 6: Advanced Risk Management (Full Bowtie Builder)

- Full Bowtie Data Model: bowtie_events, bowtie_barriers, bowtie_controls tables

- Interactive Bowtie Canvas: BowTieBuilder.tsx — React Flow/D3 drag-and-drop visual canvas, export PDF/PNG

- AI-Generated Bowtie: POST /api/ai/bowtie/generate — complete bowtie JSON from free-text hazard description

- Critical Control Verification: digital sign-off required before high-risk work begins, auditable timestamps

## 4.4 Weeks 6–7 — Module 7: React Native / Expo Mobile App

Reports: PR-11 + PR-12 (Week 6)  |  PR-13 + PR-14 (Week 7 partial)

### Week 6 — Mobile Core: Bootstrap, Offline, QR, Voice

- Expo project targeting iOS (App Store) + Android (Google Play) with EAS for build + OTA updates

- Offline Incident Capture: expo-sqlite local storage + background sync engine with conflict resolution

- Voice-to-Incident Reporting: device microphone → speech-to-text → AI pre-fills incident form fields

- QR Code Location Tagging: expo-camera scanner auto-fills location_id on incident + asset inspection forms

### Week 7 — Mobile Advanced: Camera AI, Push, Signatures, Multi-language

- AI-Powered Hazard Detection: camera frame → POST /api/ai/hazard-detection → real-time bounding box overlays

- Push Notifications (Expo Push Service): triggers for incident assigned, CAPA overdue, cert expiring

- Digital Signature capture: SVG-based signature pad — legally auditable, timestamped, stored in S3/R2

- Multi-Language Support: English, Arabic (RTL), Spanish, French — extends existing i18n infrastructure

## 4.5 Week 8 — Modules 8–10 + Technical Debt + Final Production Deploy

Reports: PR-15 (mid-week) + PR-16 (Milestone 2 Final)

### Module 8: Workflow Automation Engine

- automation_triggers table: event type, conditions JSON, actions JSON, active flag

- Multi-step workflow builder: chain actions (notify → escalate → create_capa → assign_task)

- AI-based escalation: if overdue > 5 days + severity=High → auto-escalate to department manager

- Frontend: AutomationBuilder.tsx — visual drag-and-drop condition/action builder

### Module 9: ESG & Carbon Accounting

- emissions_records table: source, Scope 1/2/3 category, value, unit, date, site_id

- ESG framework mapping: GRI, TCFD, SASB — map emissions data to reporting framework fields

- AI-generated ESG narrative reports: POST /api/ai/esg/generate-report

- Frontend: ESG carbon accounting dashboard — emissions by source, Scope breakdown, YoY trend

### Module 10: Enterprise Integrations

- SSO: Azure AD + Okta via SAML 2.0 / OIDC — admin configures in Organization Settings

- HRIS Integration: Workday / SAP SuccessFactors — bulk worker import + auto-enrollment

- ERP Integration: SAP / Oracle — asset data sync, bi-directional via REST webhook

### Technical Debt Resolution

| Item | Action |
| --- | --- |
| Migrate SQLite → PostgreSQL | Full DB migration with Drizzle ORM. Zero data loss. |
| Repository Pattern | Extract all DB access from routes into typed repository classes |
| BullMQ + Redis Worker | Provisioned in Week 3, hardened for production in Week 8 |
| Multi-tenant Schema Isolation | Add tenant_id to all tables. Row-level security middleware. |
| Rate Limiting Per Tenant | Replace IP-based rate limiter with tenant-aware middleware |
| API Versioning (/api/v1/) | Prefix all routes. Backward-compatible. Required before HRIS/ERP. |

| M2 Deliverable | Module | Week |
| --- | --- | --- |
| Audit Scheduling Engine (RRULE-based, BullMQ) | Module 3 | Week 3 |
| Multi-Site Compliance Reports + Conditional Form Logic | Module 3 | Week 3 |
| Training Matrix Engine + Gap API | Module 4 | Week 3 |
| Certification Expiry Engine + Alerts | Module 4 | Week 3 |
| AI Incident Classification (OSHA/WSIB) | Module 1 | Week 4 |
| Evidence OCR + NLP Pipeline + S3/R2 | Module 1 | Week 4 |
| AI CAPA Root Cause Suggestions (5-Why/Fishbone) | Module 2 | Week 4 |
| Predictive CAPA Prioritization Score | Module 2 | Week 4 |
| Asset Registry + QR Code Generation + LOTO Templates | Module 5 | Week 5 |
| Full Bowtie Builder + AI-Generated Diagrams | Module 6 | Week 5 |
| React Native / Expo App — Offline, QR, Voice | Module 7 | Week 6 |
| Mobile App — Camera AI, Push, Signatures, i18n | Module 7 | Week 7 |
| Workflow Automation Engine | Module 8 | Week 8 |
| ESG Carbon Accounting + AI Reports | Module 9 | Week 8 |
| SSO (Azure AD/Okta), HRIS, ERP Integrations | Module 10 | Week 8 |
| PostgreSQL Migration + Repo Pattern + Multi-Tenant | Tech Debt | Week 8 |

💰 Market Value Analysis & Why $1,750 Is the Right Price

# 5. What This Work Would Cost on Fiverr or at an Agency

Let's be completely transparent. This section breaks down the real market value of every module and component in this SOW — what a client would pay if they hired a Fiverr seller, a freelance team, or a mid-size agency to build the same work from scratch, without any prior context on the codebase.

| Module / Scope Item | Market Rate (Fiverr/Agency) | Our Price | Your Saving |
| --- | --- | --- | --- |
| Milestone 1: Full UI/UX Enterprise Overhaul (Design tokens, component library, 40+ pages, theme, responsiveness, QA) | $2,000 – $3,500 | $150 | $1,850+ |
| Module 7: React Native Mobile App (Offline sync, Voice-to-Incident, Camera AI, Push, Signatures, i18n) | $3,000 – $5,000 | $700 | $2,300+ |
| AI Intelligence & Risk Engine (Modules 1, 2, 6: Classification, OCR, CAPA AI, Bowtie AI) | $2,500 – $4,000 | $400 | $2,100+ |
| Core EHS Operations (Modules 3, 4, 5: Audit Scheduling, Training Matrix, Asset Registry) | $2,500 – 3,500 | $300 | $2,200+ |
| Enterprise Scaling & Tech Debt (Modules 8, 9, 10: Automation, ESG, SSO/HRIS/ERP + PostgreSQL + Multi-tenant) | $3,000 – 4,500 | $200 | $2,800+ |
| 📊 TOTAL | $13,000 – $20,500 | $1,750 | $11,250 – $18,750 |

## 5.1 Why Can We Offer This at $1,750?

Three structural advantages allow us to dramatically undercut market rates without compromising quality:

| Advantage | What It Means For You |
| --- | --- |
| Zero Learning Curve | A new developer would spend 3–4 weeks just understanding this codebase: the schema, the components, the API patterns, the test setup. We have already done all of that. We start from Day 1 in full execution mode. |
| Parallel Execution Capability | Because we built it, we can run multiple tracks simultaneously (e.g., building the component library while fixing the theme system). A new team would work sequentially, taking 2–3x longer. |
| Deep Domain Context | We know the EHS domain constraints, the OSHA rules, the PTW workflow logic, the AI integration architecture. No time is lost on domain research or codebase archaeology. |

🎯 Timeline Advantage — Industry Standard vs. Our Plan: The full scope of this project is an 18–20 week engagement for any standard team. Due to our deep familiarity with this exact codebase, we have mapped it into an 8-week delivery plan. We keep Week 8 as a soft buffer to account for communication delays or edge cases — but our full commitment is to complete everything within 8 weeks. This means your platform can be production-launch-ready as early as Week 7.

## 5.2 Timeline Comparison: Standard vs. Our Delivery

| Delivery Phase | Standard Agency Timeline | Our Accelerated Timeline | Why We’re Faster |
| --- | --- | --- | --- |
| Milestone 1: UI/UX Overhaul | 4–5 Weeks | 2 Weeks | No ramp-up; we know every component file |
| Module 3+4: Audit + Training | 3–4 Weeks | 1 Week | We wrote the DB schema; no design time needed |
| Module 1+2: AI Intelligence | 3–4 Weeks | 1 Week | OpenRouter already integrated; AI pipeline pattern set |
| Module 5+6: Asset + Bowtie | 3–4 Weeks | 1 Week | React Flow already in codebase; schema pattern proven |
| Module 7: React Native App | 4–5 Weeks | 2 Weeks | Shared auth/types with existing React frontend |
| Modules 8–10 + Tech Debt | 4–5 Weeks | 1 Week | Architecture decisions already made; just execute |
| 🏁 TOTAL | 18–20 Weeks | 8 Weeks (+ 1 buffer) | Learning curve reduction = pure velocity |

🚀 When Can You Launch?: After Week 7, SafetyMEG will be fully production-deployable with all 10 modules live. Week 8 is a hardening and buffer week — we use it for final integration testing, performance tuning, and any edge cases. As we complete individual modules before that, we will update you continuously so you can begin internal testing and stakeholder demos in parallel. You don't have to wait until the very end to start using the platform.

# 6. Post-Launch Maintenance — Optional Offer

🛡️ Important Consideration: SafetyMEG is an enterprise-grade platform with 95 pages, AI integrations, mobile apps, background job workers, multi-tenant infrastructure, and third-party service connections. Enterprise platforms at this level require ongoing maintenance — dependency updates, security patches, API changes from third-party providers, bug fixes from edge cases discovered in production, and feature iterations based on user feedback.

## 6.1 Why Maintenance Matters

After launch, the following categories of work arise naturally on any enterprise platform:

| Maintenance Category | Why It Arises | Risk If Ignored |
| --- | --- | --- |
| Security patches & dependency updates | npm packages release security fixes monthly | Security vulnerabilities in production |
| Third-party API changes | OpenRouter, Expo, Resend, Cloudflare update their APIs | AI features or email stop working silently |
| Mobile app updates | Apple/Google OS updates can break React Native apps | App Store removal or crash on new iOS/Android |
| Bug fixes from production use | Real user load surfaces edge cases not caught in testing | User-facing crashes and data integrity issues |
| Feature iterations | Client and user feedback drives UI/UX improvements | Platform stagnates vs. competitors |

## 6.2 Our Maintenance Offer

If you already have a development and testing team in-house, you are fully covered — no action needed. But if your team's bandwidth is limited or you'd prefer to keep the people who built this platform maintaining it, we offer a low-cost monthly retainer specifically designed for post-launch support.

| Plan | Coverage | Est. Monthly Investment |
| --- | --- | --- |
| Basic Support | Security patches, dependency updates, critical bug fixes (response within 48 hrs) | Very affordable — discuss on request |
| Standard Retainer | All of Basic + AI API monitoring, mobile app OS compatibility, 5 hrs of minor feature work | Discuss based on usage scale |
| Growth Retainer | All of Standard + priority feature development, ESG report iterations, HRIS sync tuning | Discuss based on scope |

💡 Our Advantage as Your Maintenance Partner: Because we built the platform, our maintenance cost to you is a fraction of what a new team would charge — there is zero ramp-up overhead on our side. We already know every API endpoint, every DB table, every component. What might take a new developer 4 hours to investigate, we resolve in 30 minutes. This translates directly into lower cost for you.

If you are interested in a maintenance arrangement, we can define the exact scope and pricing after the project delivery is complete and you have had time to evaluate the platform in production. No commitment is needed now — this offer stands.

# 7. Commitments, Terms & Agreement

## 7.1 Development Team Commitments

- This document will be followed strictly. No features will be added or removed without a written scope change amendment agreed upon by both parties.

- Two progress submissions will be delivered per week, each including: a Progress Report PDF, a source code commit (Git), and a live staging deployment URL.

- All code will be committed to the project repository with clean, descriptive commit messages. The client will have read access to the repository at all times.

- All new features will include appropriate backend validation (Zod), unit test coverage for critical paths, and frontend error handling.

- The development team will not use the client's production database for testing — a dedicated staging environment will be maintained throughout.

- Any discovered security vulnerability will be disclosed to the client within 24 hours and patched before proceeding with other work.

- Our full commitment is to complete all 8 weeks of work within 8 calendar weeks. The buffer week accounts for communication delays only, not development delays.

## 7.2 Client Commitments

- Provide feedback within 3 business days of each progress submission. Silence beyond 3 days constitutes implicit acceptance of that cycle's work.

- Make weekly payments on time. Development for the following week begins only after the current week's payment is received.

- Provide timely access to any API keys, credentials, or accounts required for integration work (SSO, HRIS, ERP).

- Not commission duplicate work from another party on the same features during the active milestone period.

## 7.3 Scope Change Protocol

If the client wishes to add, remove, or significantly modify any feature within an active milestone:

- Client submits a written change request describing the desired modification.

- Development team responds within 3 business days with impact assessment: effort change, timeline change, and cost change.

- Both parties must confirm via email before work proceeds.

- If the change increases scope significantly (>20% effort), it may be moved to a new milestone.

## 7.4 Timeline Summary

| Week | Milestone | Key Work | Reports |
| --- | --- | --- | --- |
| Week 1 | M1 | Design tokens, typography, color palette, dark/light theme fix, logo & button unification | PR-01, PR-02 |
| Week 2 ✅ | M1 Final | SM* Component Library, skeleton loaders, toast system, mobile responsiveness, accessibility QA | PR-03, PR-04 |
| Week 3 | M2 | Module 3: Audit Scheduling Engine + BullMQ/Redis setup ¦ Module 4: Training Matrix + Cert Expiry | PR-05, PR-06 |
| Week 4 | M2 | Module 1: AI Incident Classification + OCR/NLP ¦ Module 2: AI CAPA + S3/R2 setup | PR-07, PR-08 |
| Week 5 | M2 | Module 5: Asset Registry + LOTO + AI Risk Scoring ¦ Module 6: Bowtie Builder + AI Generation | PR-09, PR-10 |
| Week 6 | M2 | Module 7 Part 1: React Native bootstrap, offline sync, QR scanning, voice-to-incident | PR-11, PR-12 |
| Week 7 | M2 | Module 7 Part 2: Camera AI hazard detection, push notifications, digital signatures, multi-language | PR-13, PR-14 |
| Week 8 ✅ | M2 Final | Modules 8–10: Automation Engine, ESG Carbon, SSO/HRIS/ERP ¦ Full tech debt ¦ Production deploy | PR-15, PR-16 |

🎯 Launch Window: Platform is production-launch-ready after Week 7. Week 8 is final hardening. As modules complete earlier than scheduled, you will be continuously updated and can begin stakeholder demos from Week 2 onward.

## 7.5 Closing Statement

SafetyMEG is already an impressive platform — a testament to the development effort invested. What this roadmap does is take a technically capable product and elevate it to the commercial and operational standard that enterprise EHS clients expect.

At $1,750 for work that would cost $13,000–$20,000 on the open market, and delivered in 8 weeks instead of 18–20, this represents one of the highest-value arrangements a client can enter into with a development team. The reason we can offer this is simple: we know this codebase inside and out. Your learning-curve savings become our ability to price fairly and deliver fast.

We are committed to delivering every item in this document to the standard described, on time, with transparent communication throughout. We look forward to building the next chapter of SafetyMEG together.

| Party | Signature | Date |
| --- | --- | --- |
| Development Team Sign-Off | _________________________________ | ________________ |
| Client Sign-Off | _________________________________ | ________________ |